## 8 May 2013
Project | Progress I made today | Deadline | on target
photographer searching | the lowest is RMB30, I got 2 contacts, sent each of them 2 products for photoshooting for a test to them , the express will take 2 days | 2013-05-23
all the XBOX/ SONY/ EARPHONE suky purchased to be sent to 4px with labels and greeting cards | products with labels ready, just the greeting/freebie card is pending | 2013-05-22
quotation asked | all the price inquiries sent to the vendors and suky, with confirmation of the MOQ | 2013-05-23
package purchasing | package confirmed with max- prepare purchasing of the right size packing bags | 2013-05-22
flat files of our new bundles | Started prepare the flat files of our new bundles
Making a promotion plans for those bundles | just started, but need to confirm with the suppliers first if the small tools pack available | 22nd
promotions for old products in stock | not yet started | 22nd